## Lessons Learned Register
Mandatory Fields | [7 empty] | Optional Fields
Title | Description of Driving Event | Lesson Learned | Recommendation | Organization |  |  | Lesson Date | Submitter by information | Point of Contact | Abstract | Evidence of recurrence control effectiveness | Any safety issue the lesson addresses | Privacy preference | Lifecycle Phase | Submitter's role in Program / Project | Categorization | Additional key words | Applicable NASA Mission Directorate | Previous Documentation of Lesson Learned | Restrictions on data | Relationships to particular NASA policy, standard, handbook, procedure, etc. | Year of occurrence | Message to reviewer
|  | Lesson |  | Program | Project | Instrument | [17 empty] | Subject Matter Category | PMP Process | SE Process | Remarks
|  | Guard against false valid command blocks |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Plan Risk Responses | Technical Risk Management
|  | Process for bringing in new products needs to be streamlined because of the current 3-year proposal cycle |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Plan Procurements | Product Implementation | Ocean group has developed a well-defined process that allows for community feedback
|  | Multiple contractors performing algorithm implementation is problematic |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Conduct Procurements | Product Implementation
|  | CALIPSO levered off existing ASDC infrastructure provided by CERES |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Direct and Manage Project Execution | Product Implementation | CNES L1 IIR algorithm team whote spec; L2 IIR algorithm team (IPSL) integrated science algorithm into NASA-provided production test harness; NASWA DMT responsible for all production code
|  | Third party XSAN online disk storage is problematic |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Direct and Manage Project Execution | Design Soluition Definition | Expanded production online storage from 4TB to 32TB w/ XSAN; Initial XSAN NFS implementation corrupted HDF files
|  | XSCN Problems |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Monitor and Control Risks | Technical Risk Management | Mitigated problem by performing critical I/O to direct attached SGI RAID, added automatic QC file check prior to archive, only copy to XSAN; ASDC XSAN disk failure caused loss of browse images (3 mos.), LSWG analysis and working copy of data; ASDC replacing XSANs with large (>1 PB) IBM GPFS disk arrays
|  | Small random I/O performance issue in selection of Linux cluster |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Direct and Manage Project Execution | Product Implementation
|  | Science code software engineering process needs “facelift” – better use of integrated automated tools for requirements traceability, design, versioning, and verification |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Define Activities | Logical Decomposition
|  | As data systems become more complex and distributed need better systems engineers not just science programmers |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Manage Project Teams | N/A
|  | 4X throughput not enough for reprocessing; the goal should be >12X |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition
|  | Linux upgrade slower than expected – operations taken precedence |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Data Processing | N/A | Product Implementation
|  | Make real-time data access (Quicklooks) a high priority/requirement … if for no other reason - anomaly identification and resolution by C&C and Instrument teams… it will also be used extensively by science teams |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition
|  | We cut integration time significantly by requiring that each algorithm team use a specific software development environment and programming language … and also by providing each team with a common development system that allowed them to interface seamlessly with all other developers and the data processing center |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Data Processing | N/A | Product Implementation
|  | When relying on ancillary data to generate your products … allocate sufficient time/resources for coordination with all ancillary data providers and formation flying partners …this was a greater effort than expected due to changes by other missions (data formats / media upgrades / reprocessing schedules / operational release schedules, etc.) |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Data Processing | Estimate Activity Durations | Technical Planning
|  | Make software interface tools a very high priority and expedite with on-line tools (such as the “AIMS” interface – which was indispensible …). If done properly, these interface tools will greatly simplify software integration, configuration control, and ops-phase revisions. |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Data Processing | N/A | Interface Management
|  | Using Similar data format saved time and cost |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition | In the early communications with JAXA (then NASDA) Data team, the US Data team (TLSCF and SIPS) was able to convince them of the usefulness of using same data formats (HDF file format); there were some minor changes instituted by both sides, and good communications between the Data teams made all of them transparent; data latency is between 4 and 10 hours, much lower than in the early days of the mission.
|  | Slow processing rates had an undesirable impact to users |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Data Processing | N/A | N/A | The slow processing rates of the SIPS computers did not allow for reprocessing from the beginning of the mission every time a new version of the algorithm was implemented; users did not have a consistent product set.
|  | NSIDC DAAC Results |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Data Processing | Plan Communications | Technical Planning | Positive: Good communications (written agreement document with roles and responsibilities, as well as email, telecons,…) between the DAAC and SIPS imperative for success of the mission; Positive: Product Acceptance Notice (PAN)-based data reconciliation process worked very well (should be considered for future SIPS-DAAC environments); Positive: On-line access to products reduced the data distribution level-of-effort and improved user satisfaction; Undesirable: ATBDs available to users were not kept up-to-date (later updated with “short ATBDs”); Undesirable: Delivered Algorithm Packages (DAPs) do not have a standard development environment (supporting users attempting to run all DAPs can be costly).
|  | Keep data systems distributed and as focused as possible to be robust and less complex. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition
|  | Costs of data systems increase nonlinearly with complexity but savings from elimination of "redundancy" are only linear. This suggests that the most robust cost effective system will be distributed and not centralized. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Estimate Costs | Design Soluition Definition
|  | Data production and archiving are "industrial strength" activities that need a critical mass to achieve high reliability: this suggests the minimum size for data centers. Overall the ~10 EOS distributed data centers seems to have been an effective and robust approach in this "middle ground”. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition
|  | SCF RAID lessons learned: Consumer grade RAID arrays are not yet sufficiently robust and reliable for serious archiving. Suggests that at least triple redundancy may be needed for use of such "cheap" disk. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Plan Procurements | Product Implementation
|  | Must have dedicated ASDC personnel who focus primarily on CERES data processing. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Develop Human Resource Plan | Technical Planning
|  | Updating production code is time and resource consuming due to rigorous procedures and testing, but taking shortcuts or circumventing procedures in the long run results in wasted time and effort. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Estimate Activity Durations | Product Implementation
|  | ASDC production is limited to number of staffed operators, not available CPUs. Operations are still done manually. Big problem getting to automated processing in past was ensuring all needed inputs were available on disk. Automation expected to substantially increase operation. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Develop Human Resource Plan | Design Soluition Definition
|  | Having a staff-member focused primarily on CERES data processing improved coordination between the various groups and mitigated problems. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Develop Human Resource Plan | Technical Planning
|  | Data Management testing of a code delivery prior to releasing the software to the ASDC minimizes problems identified during operational testing. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | Perform Quality Assurance | Product Verification
|  | Not following the coding guideline will get the code into production faster in the short run, but in the long run, when it's time to move to another platform or make modifications, the required resources will be much greater. It's a game of pay now, or pay later with interest. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Data Processing | N/A | Product Implementation
|  | Build for generality. Identify requirements up front, but expect that the needs of production will be different from what you expect. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Good software practices – identify and allow for those things which are likely to change. Make as much configurable and table-driven as practical. This requires both foresight and luck! We had both.
|  | Recognize and accommodate differences between research and production data processing |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | Define Activities | Logical Decomposition | The science code is typically developed by one or two expert developers per module. Choose the size and number of modules accordingly. Design to allow insertion of additional modules as needed for new functionality. A larger team with collaborative development was well-suited to the data management and process scheduling software, allowing us to create a complex system with rich metadata documenting the provenance of the data. Expect that the operators of the system and the users of the science data will require different interfaces and views of the data.
|  | Standardize and test interfaces early |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Interface Management | Aura File Format Guidelines standardized file structure of data products from all Aura instruments. Arriving at consensus required much persistence and diplomacy, but it was repaid with easier collaboration after launch. Processing modules were required to conform to a standard interface within the SIPS production system, making it easier to release, install and track new modules.
|  | Prior experience with similar instruments, and the ATBD, are very important. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | Develop Human Resource Plan | Technical Planning | Previous experience on LIMS, ISAMS and CLAES , MOPITT was very useful; ATBD’s were useful exercise; L0-L1: Pre-launch Oxford; transitioned to NCAR after Kapton anomaly; Many changes necessitated; L1-L2: NCAR/UCB (note needed L2PP to interface); Few changes
|  | An early start on software development is essential. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | Sequence Activities | Technical Planning | Even so not everything was in place before launch; Early development of approximate Forward Radiative Transfer Model for engineering purposes is essential; Subsequent development of 2 accurate RTM’s for data retrieval
|  | For a number of data products more than one product has been produced. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Data Processing | Manage Stakeholder Expectations | Stakeholder Expectations Definition | Has led to several improvements of the algorithms; Important to communicate to the user which datasets fits their needs the best.
|  | The close collaboration and rapid feedback between the Level 1B and Level 2 groups is essential. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Data Processing | Plan Communications | Technical Planning
|  | To improve the consistency between data products (consistent retrieval algorithms and diagnostics) the OMI product based organization should be reconsidered. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Data Processing | N/A | Technical Planning
|  | Technological improvements led to increased productivity |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Product Implementation | Migration to Linux; Simplified manageability (one software base instead of three); Improved throughput with cheaper commodity hardware; Faster generation of products – completion of reprocessing. Evolution from tape-based to disk-based archives: Improved data access and throughput; Greater reliability; Corollary: There is NEVER enough disk storage space!
|  | Release new products to meet changing customer needs |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Data Processing | Manage Stakeholder Expectations | Stakeholder Expectations Definition | AIRS near-real-time from GES DISC; Increased user interest in NRT AIRS product could not be supported by NOAA; GES DISC worked with JPL and NOAA to develop local support at GES DISC; GES DISC routinely produces L1B and L2 products exceeds throughput achieved by NOAA
|  | Consider reprocessing carefully |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Data Processing | Perform Integrated Change Control | Requirements Management | Reprocessing campaigns are not free. Resources consumed must be weighed against value of a new product; Bringing a new product to market involves hidden costs… it’s not just product development we must consider: Integration and test, Validation, Installation and checkout at Customer’s site (e.g., GES DISC), and Time to process; Impact to end-user must also be carefully weighed: consistency and continuance of long-term data record is important, time to acquire a new data record must be considered.
|  | Unique data permits new phenomena to be seen, and more detail added to knowledge of known processes |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition | The HIRDLS data are unique in their high vertical resolution and ability to see atmospheric particulates. Had it not been for the Kapton problem, the HIRDLS data would have led to an very large number of contributions and new insights on hitherto unobserved atmospheric phenomena. The 3 years of HIRDLS data provide an outstanding set of observations that is just beginning to be exploited.
|  | Forward Processing should be at least 2X (2 times real-time) for catch-up |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Must not be network limited
|  | Build a scalable system (from 2X to 10s of X) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Plan Procurements | Product Implementation | Buy hardware as late as possible to take advantage of Moore's Law and pricing
|  | Build to run on commodity hardware – not a super computer |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Benefits: easier to scale, cost savings and easier technology refresh
|  | Having done Terra made Aqua data processing a lot easier |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | N/A | Mainly had to scale end-to-end system that already worked
|  | Pre-launch End-to-end testing of data flow is needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Plan Quality | Product Validation | Good proxy/simulated data is valuable (for Aqua we used Terra plus some simulated data); Rehearsals: go from day in the life to week in the life, etc.
|  | A reconciliation process is needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Perform Quality Assurance | Product Verification | Data flows between data centers must be checked and verified on an on-going basis (see Murphy’s Law)
|  | Monitor data flows and production metrics to identify bottlenecks and optimize use of resources (adding/moving processing nodes, etc.) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Perform Quality Assurance | N/A | For Ocean Color, adapting the heritage SeaWIFS algorithm for Aqua made it possible to produce a good quality product
|  | It was useful to have same algorithms across multiple sensors |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition
|  | Reprocessing: It should be possible do a minimum of entire mission in 1 year |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | 2X forward plus more than 1X per mission-year; Ideally should be able process mission in 3 months or less (requires 10X to 100X); Having Level 0 data on-line makes science testing and reprocessing much easier; Disciplines will have their own reprocessing schedules; So the reprocessing data system needs to be able to handle this; Multiple strings may be needed for individual disciplines
|  | Test system (separate string) should be minimum of 1X; ideally 4X to 10X |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Can double as reprocessing string
|  | Science testing: Don’t bundle too many changes together – impacts of upstream algorithms are hard to untangle |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Logical Decomposition
|  | Science testing: Many iterations of testing are needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Perform Quality Assurance | Product Verification
|  | Science testing: Storage is needed for multiple baselines and changes |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Estimate Activity Resources | Technical Data Management
|  | Science testing: Carefully control for ancillary data dependencies |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition
|  | Science testing: Maintain a basic set of science test days |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Technical Data Management
|  | Over the life of the mission, porting to new systems (e.g. IRIX to Linux) will be necessary, but should be kept to a minimum |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Plan Risk Responses | Technical Risk Management | Build portability into software; Changes to compilers, libraries and data system may also need to be tested; Porting requires careful evaluation and key human resources – but it is not of primary interest to the science team
|  | Key communities will need specialized products |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Logical Decomposition | Products in Climate Modeling Grid for climate modelers; Near Real Time products for applications users; Plan for additional formats and tailored products; One map projection (grid spacing, etc.) will not work all users (or even a majority)
|  | Self document format (HDF) is useful – but additional formats are needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Geographic information system users have community format standards (not HDF)
|  | Always have a full collection going forward |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | Define Scope | Technical Requirements Definition | Reprocess the full mission in background; Give users time to switch over to new dataset
|  | On-line products (including Level 0) greatly increased distribution |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Data Processing | N/A | Design Soluition Definition | Made getting data much easier and increased speed of fulfilling orders; Enables processing-on-demand for tailoring products as well as web services; Need to perform trade study between processing-on-demand vs. storing products on a product by product basis
|  | Targeted outreach program is needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Education and Public Outreach | Manage Stakeholder Expectations | Stakeholder Expectations Definition | Imagery support is needed for outreach; Earth Observatory for one-stop shopping – must include good descriptions (captions) – this is a good way to deal with the Media
|  | If at all possible, build a complete end‐to‐end engineering model, including all of the software, and test it as thoroughly as possible as early as possible |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Hardware Development | Verify Scope | Product Verification | For an instrument such as MLS which has several very similar signal paths, the engineering model need only implement one or two such paths. Simulators can often be used to emulate the missing subsystems (useful for software testing)
|  | All of our critical intermediate frequency (IF) signal processing chains were so poorly manufactured that we had to switch vendors between engineering and flight models, with resulting loss of heritage |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Hardware Development | Verify Scope | Product Verification
|  | Don’t use military grade IMU for space mission if needed for extended period |  | ESSP | GRACE | [12 empty] | Science | [5 empty] | Hardware Development | Conduct Procurements | Product Implementation
|  | Power dissipation of individual components, and timing margins, should be estimated during the design phase |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Hardware Development | N/A | Design Soluition Definition
|  | Stable calibration and algorithms are needed to produce a good time series |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | Plan Quality | Product Verification | Don’t make changes in middle of reprocessing; Minimize changes in forward processing (after calibration and algorithms stabilize)
|  | Aqua had much better algorithms after Terra – end-to-end flow already tested |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | Plan Quality | Product Verification
|  | Improved Aqua instrument characteristics made some products possible, e.g. Ocean Color, Deep Blue Aerosols |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | N/A | N/A
|  | Ask for more money when building a high voltage power supply |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Instrument | Estimate Activity Resources | N/A
|  | Include the number of HPA trips in telemetry |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Instrument engineering telemetry simulation software needs to be budgeted for and implemented |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Instrument | Estimate Activity Resources | N/A | The EOC has an excellent spacecraft simulator; Its instrument fidelity is weak
|  | For cold instruments, hardware design must include proper venting and elimination of outgassing products |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | Warming the instrument to eliminate ice build up only works temporarily because the water vapor has nowhere to go
|  | Two coolers are better than one |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | Using the two AIRS coolers simultaneously actually lengthens projected instrument life
|  | Instrument operation and calibration procedures need to be followed strictly and updated as needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | N/A | Product Implementation
|  | Operation concept document needs to be peer reviewed and updated periodically |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | Verify Scope | Stakeholder Expectations Definition
|  | Successful on-orbit operation/calibration relies on vigorous pre-launch characterization and testing effort |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Instrument | Perform Quality Assurance | Product Validation | Improved TEB Response Versus Scan Angle; Reduced SWIR cross-talk; eliminated PC bands optical leak at pre-launch; SDSM misalignment issue well understood (from Terra MODIS as well); better prepared for on-orbit mitigation; Impact due to 2 known problems (inoperable detectors in band 6; BBR between warm and cold FPAs)
|  | OMI successfully demonstrates the use of 2-D detectors for nadir viewing solar backscatter spectrometers. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | N/A | Product Implementation
|  | The optical degradation is the lowest of UV instruments launched. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | N/A | Product Implementation
|  | The wide angle telescope, the polarization scrambler and the QVD solar diffusor were all successful. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | N/A | N/A
|  | Unique on-ground calibration measurements (i.e. stray light measurement) have to be measured at various angles and for inflight representative conditions. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | Perform Quality Assurance | Product Verification
|  | Measurement of the instrument spectral response (slit) function was successfully performed and has preference over gas cell measurements. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | N/A | Product Verification
|  | Effects of detector degradation (RTS effects) on Level 2 data products should be minimized by frequently updating dark current maps and lowering the detector temperature. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | Plan Risk Responses | Technical Risk Management
|  | Solar irradiance measurements and other calibration measurements should have a SNR much higher than the radiance data to avoid stripes in the data products. |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Technical Requirements Definition
|  | End-user involvement important during the instrument development (Direct feedback from scientists) |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Instrument | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | A very low level of non‐linearity (<1% gain compression) translates into significant errors (up to several Kelvin) in calibrated radiances when the scene has high spectral content |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | When an instrument works extremely well, however hard one worked at pre‐launch calibrations, it will not have been hard enough |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Instrument | Perform Quality Assurance | N/A
|  | Do not accept requirements blindly |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Instrument | Collect Requirements | Technical Requirements Definition | In this case the radiometric calibration system met requirements, but should have been better.
|  | Science team involvement in instrument I&T was extremely valuable; less of dividing line between science & engineering |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Develop Human Resource Plan | Technical Planning | Avoided ‘throw it over the wall’ mentality; Science was involved with issues immediately & intimately; Science & Ground System involved in processing data from I&T
|  | Very public I&T schedule |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Control Schedule | Technical Planning | Awareness of responsibilities & delivery dates
|  | Interferometer Control Subsystem (ICS) bearing design specified insufficient amount of lubricant & inadequate lubricant retention |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Technical Requirements Definition | Type and quantity of lubricant chosen for design prioritized low temperature velocity control performance over life. Encoder CDR Action Item #1 (4/98) documented the concern with bearing lubricant life, offered recommendations, and maintained the importance of consistent and predictable low friction
|  | ICS life test ran at accelerated rate; even so results came too late to impact ICS integration |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Estimate Activity Durations | Technical Planning | Estimate to replace bearing 12 MY / 1 year
|  | ICS Lube Macro introduced to redistribute remaining lubricant |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Aura project accepted the ICS risk & decision to ‘fly as-is’ |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Plan Risk Responses | Technical Risk Management | TES continues to operate with a modified operational plan & return unique and valuable science data. TES has over 5.1M scans
|  | Pointing Control Subsystem (PCS) Mission design lifetime of 5 years is within the flex cable lifetime estimate of 1M cycles ( TES has slightly over .8 M cycles ). |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Technical Requirements Definition
|  | PCS subsystem achieved minimum success criteria & design lifetime of 5 years + ground testing. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | N/A | N/A
|  | Concern on PCS flex cable were raised early in design cycle (ADEOS life-test unit failure); concern addressed by manufacturer & accepted. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Plan Risk Responses | Technical Risk Management
|  | Modeling of blackbody calibration data soon after launch could have identified opportunity to greatly reduce number of blackbody scans & the exercise of PCS cross track flex cable. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | Identify Risks | Technical Risk Management
|  | Ability to gather high rate data on PCS movement & current was instrumental in identifying issue & resolving it. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Overlapping missions (e.g., future TSIS and SORCE) are required until solar irradiance accuracies are improved to 100 ppm |  | ESMP | Aura | SORCE | [11 empty] | Science | [5 empty] | Instrument | Manage Stakeholder Expectations | Stakeholder Expectations Definition | TIM (4-channels) degradation understood to better than 10 ppm/year; SIM degradation understood best from SIM-A & -B comparisons
|  | Pre-flight calibration accuracy can be improved by using multiple calibration techniques / references |  | ESMP | Aura | SORCE | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | XPS calibrations improved by combining 3 different calibration sets; New NIST SIRCUS facility will greatly help to improve calibration accuracies in the NUV-VIS-NIR (e.g. for future SIM); New TSI radiometric calibration facility developed at LASP for Glory TIM
|  | Results can be significantly improved with higher spectral resolution |  | ESMP | Aura | SORCE | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | Solar Mg II index improved with SOLSTICE’s 0.1 nm resolution; XPS analysis would be easier with higher resolution
|  | Higher spectral resolution improves measurement of Mg II index. |  | ESMP | Aura | SOLSTICE | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Stakeholder Expectations Definition | This is being incorporated into the design of the NOAA GOES-R solar instrument.
|  | Redundant channels not only ensure against data loss, they also improve understanding of instrumental changes during a long mission. |  | ESMP | Aura | SOLSTICE | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Technical Requirements Definition
|  | Use multiple calibration techniques / references to achieve best accuracy |  | ESMP | Aura | XPS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Easier to interpret results with higher spectral resolution |  | ESMP | Aura | XPS | [11 empty] | Science | [5 empty] | Instrument | N/A | Technical Requirements Definition | Data processing results can be dependent on spectral models when working with broad band photometers
|  | Filter Wheel Mechanisms should use direct drive, or at least few gears |  | ESMP | Aura | XPS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Filter Wheel Motor control should have forward/reverse direction and, if possible, redundant winding |  | ESMP | Aura | XPS | [11 empty] | Science | [5 empty] | Instrument | Define Scope | Technical Requirements Definition
|  | Braycote (wet) lubrication is better for gears that dry lubrication |  | ESMP | Aura | XPS | [11 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition
|  | Key Aqua instrument issues (no instrument is a perfect clone): Band 6 dead detectors caused changes in some algorithms (e.g. cloud mask, snow) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Verification
|  | Key Aqua instrument issues (no instrument is a perfect clone): Band to band registration problem had an impact on some algorithms (e.g. aerosols) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Verification
|  | EPS Lessons learned: commandable re-charge ratio in FSW,…have backup I&T system at launch, for contingency data retrieval. |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Integration and Test | N/A | Design Soluition Definition
|  | Instrument integration challenges can be mitigated by integrating instrument engineering models with the bus avionics test bed |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Integration and Test | Plan Risk Responses | Technical Risk Management
|  | Where ICD requirements cannot be produced in the test system environment, institute additional review to ensure clear interface requirements definition and common understanding |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Technical Assessment
|  | Where possible, have the hardware designer provide the software that goes with hardware that contains an embedded processor. This forces the designer to make the effort to design the hardware to work efficiently in the intended application. If the software task is a large one, then have the hardware designer provide sufficient software to demonstrate that the hardware works in the intended environment |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | N/A | Product Integration
|  | If at all possible, press for a rapid prototype (hardware and software) which has just sufficient functionality to allow end‐to‐end testing, and includes both data and command flow. Details can be added later |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Product Verification
|  | Reliability does not come from after‐the‐fact analyses performed by 'reliability/parts experts' ‐‐ it comes from experience and common sense during design |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Design Soluition Definition
|  | Remember that radiation hardness concerns are going to be problematic, especially if you have a group whose job it is to handle this kind of thing (they tend to be conservative, and love to perform expensive, and time consuming, radiation testing) |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | Define Scope | Technical Assessment
|  | Calibration should not only be end‐to‐end wherever possible, but should include the use of signals which look as much like the science signals as possible |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Product Validation | This was not the case with Aura MLS, and although the calibration data looked comprehensive and wonderful. Since we could not simulate atmospheric signals closely, we overlooked a significant source of systematic error (gain compression/nonlinearity) in the pre‐launch calibrations. The non‐linearity was simply not visible with spectrally flat, broad band calibration signals
|  | Be sure in ATLO there is a USO power-on test with no backup power cable. |  | ESSP | GRACE | [12 empty] | Science | [5 empty] | Integration and Test | Close Project or Phase | Product Transition | For GRACE there was an auxiliary power supply used in ATLO in order to avoid multiple power cycles of the USO. The auxiliary power was provided (through diodes) in parallel with the S/C power. There was no USO test after the auxiliary cable was removed
|  | Include constraint checking and validation scripts to simplify Project Database (PDB) checkout |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Product Validation
|  | Should be funded as an integral part of the product development |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Estimate Costs | Product Validation
|  | Some centralized validation coordination is needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation | Makes effort more cost effective
|  | Five stage product maturity and validation approach works well |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation | Beta, Provisional, Validated Stage 1 to 3; helpful for provisional data to be available for community feedback
|  | Land: high resolution imagery and subsets for core validation sites were valuable |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Product Validation
|  | Validation should not happen too soon after launch |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | Sequence Activities | Product Validation | Products need to be stable; Aqua products were more mature before validation occurred
|  | Useful to have Near Real Time images to support validation campaigns |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Integration and Test | N/A | Product Validation
|  | Developing the validation plan forced us to think about this early |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Technical Planning | Although many things were different after launch, and did not go as we expected, the preparation was helpful; Some of the most useful data was research data that we got through non-standard paths; As expected, there was a a large amount of data for T, O3 and H2O, much smaller amounts for some of the other species.
|  | Satellite data was extremely important, because of its spatial information as well as the mixing ratios. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Verify Scope | Product Validation
|  | During the A/C missions it was important to have people at the base to take part in mission planning |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Develop Human Resource Plan | Technical Planning
|  | The AVDC was a useful as a central coincident-data repository, but it was initially difficult to assess large datasets conveniently |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | N/A | Technical Data Management
|  | Having people at many institutions was big help |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Develop Human Resource Plan | Technical Planning | This provided a wider range of skills and Insights; It also provided access to special research data sets
|  | Communications between NASA and JAXA: An interpreter present at meetings was very useful in the first three years of the mission |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning
|  | Communications between NASA and JAXA: Face-to-face meeting very important in understanding the issues |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Management | Plan Communications | Technical Planning
|  | Communications between NASA and JAXA: Joint NASA-JAXA meetings included the Data teams (TLSCF, SIPS, NSIDC) |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Management | Plan Communications | Technical Planning
|  | Communications between NASA and JAXA: A written copy of the points of discussion before the telecon proved to be useful |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Management | Distribute Information | N/A
|  | Level 1 requirements need to be written in such a way that each requirement is quantitatively verifiable. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Collect Requirements | Technical Requirements Definition
|  | Algorithm, data processing and calibration team funding and management are frequently sacrificed during cost overruns. The negative impact on the science effort should be assessed and quantified to the extent practicable (e.g. increased uncertainty in the product, increased product latency, delayed product availability, etc.) |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Control Costs | N/A
|  | Keep the team focused; Provide Clear Metric; No single point failure the system; Good communications essential; Quick: 30 mins rule; Seamless interface between HQ, Program Office, Performing Center and Contractor; Always make progress |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Manage Project Teams | N/A
|  | Form a solid project team early in the project life. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning
|  | Develop a good working relationship between the project and the science team/Project Scientist. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Manage Project Teams | N/A
|  | Develop a Functional Requirements Document and get agreement with the Science team, Project Scientist, Project Team, Lab. Management and the Sponsor. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Manage Stakeholder Expectations | Logical Decomposition
|  | Develop the Project Plan early with agreement from the Project/Science Teams, JPL Management and the Sponsor. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Develop Project Management Plan | Technical Planning
|  | Have solid concepts for the instrument design approach available early in phase A. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | N/A | Design Soluition Definition
|  | Identify long lead technology development needs and possible contractor sources |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Estimate Activity Durations | Product Implementation
|  | Get a procurement specialist on board early to support the development of the procurement plans. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Plan Procurements | Technical Planning
|  | Get a Financial Manager on board to support the budget planning/schedule process early in the project life cycle. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning
|  | Plan up-front the Quality assurance/Reliability/Safety Plans are in work and the requirements are understood (NASA & JPL). |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Plan Quality | Technical Planning
|  | Share the planning progress with the Project Scientist, Science Team, JPL management, and the Sponsor on a on going basis. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Distribute Information | Technical Planning
|  | Early on, do the make – buy process for contractor evaluation/selection or JPL in house build |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Plan Procurements | Product Implementation
|  | Analyze the design early to avoid problems in the flight build. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | N/A | Design Soluition Definition
|  | Start the test/flight software effort early to “test as we fly/ fly as we test” |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Sequence Activities | Technical Planning
|  | Have a solid configuration management system in place to control the design/development process and good electronic records storage with easy retrieval processes. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Perform Integrated Change Control | Configuration Management
|  | Hold reviews on schedule with solid follow-up on action items. |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Verify Scope | Technical Assessment
|  | Keep a good trusting working relationship with your Sponsor, JPL and NASA HQ |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Manage Stakeholder Expectations | N/A
|  | Be prepared for many re-plan cycles because of problems and budget/schedule constraints |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Estimate Activity Durations | Technical Planning
|  | Schedules need to allow far more time for pre-launch operations testing than has been allocated in the past |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Management | Estimate Activity Durations | Technical Planning | The AIRS operations team only completed pre-launch activities on time because of slips at the spacecraft contractor
|  | Combining experiments with two or three widely separated organizations in lead positions has up sides |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Define Scope | Technical Requirements Definition | More expertise, more ideas ; Costs can be shared
|  | Combining experiments with two or three widely separated organizations in lead positions has down sides |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Define Scope | Technical Requirements Definition | Longer time to reach consensus; More effort needed on communication; More time spent on travel; ITAR: Slowed down information exchange, Occasionally impeded efforts, required extra overhead
|  | Clear lines of communication and responsibility crucial |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Plan Communications | N/A | HIRDLS is a collaboration between equal partners in the US and UK, involving many organizations and separate funding agencies.
|  | No traditional lines of contractual direction to rely on when working with the UK organizations. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Plan Procurements | Technical Planning
|  | Needed an approach that enabled consensus decision making between the US and the UK. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Manage Stakeholder Expectations | N/A
|  | We established management and technical coordination teams to ensure effective work assignments, information flow, and decision making. These teams consisted of a representative from each organization, and were chaired by the lead PM and lead technical manager, respectively. |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Plan Communications | N/A
|  | When organizations are funded by different sources, need to synch up funding profile |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Determine Budget | N/A | When the launch date was delayed 4 years from 1998 to 2002, funding in the US was at a low level. However, the UK funds were already allocated and the UK organizations needed to proceed with the work. Freezing subsystem requirements and interfaces early was needed to enable the UK to start fabrication, but was hampered due to the low level of funds on the US side.
|  | Make information readily available, provide central source |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Distribute Information | N/A | A centralized database was employed to control documentation and provide information. Plan for adequate resources to upkeep (especially with ITAR).
|  | Monitor, monitor, monitor (get use to jet lag!) |  | ESMP | Aura | HIRDLS | [11 empty] | Science | [5 empty] | Management | Monitor and Control Project Work | Technical Assessment | Status telecons were held weekly. The lead program manager, technical manager and system engineer conducted regular on-site visits (4-6 weeks) at each of the organizations.
|  | Great benefit to Flight Operations Team interaction with manufacturer pre-launch |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Management | Plan Communications | Technical Planning
|  | The Memorandum Of Understanding (MOU) and the Project Implementation Plan (PIP) were written before launch |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Management | Plan Communications | Technical Data Management | The PIP did not have all the details needed (assign clear responsibility for calibration, …); the PIP was not updated since it was first approved; an updated version is going through signature approval at this time.
|  | NASA and CNES have developed effective communications across multiple levels of interaction |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Plan Communications | N/A
|  | Face-to-face meetings are crucial at maintaining continuity with personnel changes – it's very important for international relationships |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Plan Communications | N/A
|  | The annual REVEX review is a healthy and valuable exercise for the project |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Plan Communications | Technical Assessment | Facilitates engineering discussions between team members; Keeps management informed and promotes key actions
|  | Good leadership and regular communication are needed |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Manage Project Teams | N/A
|  | Weekly technical team meeting keeps everyone on same page |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Plan Communications | N/A | Consists of team leader, discipline leads, instrument/calibration lead, data system leads and outreach lead
|  | Full Science Team meetings should occur twice per year early in mission (once per year later) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Plan Communications | N/A
|  | There should be weekly calibration and data system meetings |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Plan Communications | N/A
|  | Science Team members funded before and through the life of the instrument – a long term commitment and experience base is critical |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Determine Budget | N/A
|  | Close working relationship between data team and science team members is important |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Manage Project Teams | N/A
|  | Discipline representatives provide important feedback because they understand calibration and its impact on fundamental (upstream) science products (e.g. water leaving radiance, land surface temperature, land surface reflectance, aerosols) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Acquire Project Team | N/A
|  | Having the Science Team supported and functioning well both several years pre-launch and post launch has proven wise and essential in achieving overall success |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning
|  | Direct Broadcast: Contracts and grants have to set up to allow transfer of code to users recognizing patent rights, copyrights, intellectual property rights, etc. |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Plan Procurements | Product Implementation
|  | Direct Broadcast: Contractors and grantees providing science algorithms must not use their own existing code as a module or building block for their deliverables unless the organization has no issue in making this publically available. |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Plan Procurements | Product Implementation
|  | Direct Broadcast: A direct broadcast (DB) product will not be identical to the corresponding global counterpart being held at the DAAC. Therefore a close working relationship must exist between the algorithm developer (scientist) for subsequent validation of the DB algorithm product prior to distribution to the public. |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | Direct Broadcast: Provide tools along with the DB science algorithm that would allow for its product to be reformatted (with appropriate meta-data) into a format that can be used and imported into a GIS (e.g., GeoTiff and color scale). |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Define Scope | Technical Requirements Definition
|  | Direct Broadcast: All science algorithms, no matter how big or complex, must comply to a standard invocation interface; i.e., run the same way using a “Science Processing Wrapper”. |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Define Scope | Interface Management
|  | Direct Broadcast: Software Usage Agreement (SUA) has to be (and has been) approved by Legal Counsel including saying that copyright belongs to the Government. |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Conduct Procurements | Product Implementation
|  | Dedicated science team needs to be formed and engaged with the contractor during instrument design and development stages |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning | Science-oriented individuals on the Science Team or Project Scientist Team for project management and early engineering test data analysis
|  | A calibration team (MCST), in support of science team, needs to work closely with the contractor (e.g., SBRS) for instrument pre-launch calibration and characterization |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Verify Scope | Product Verification | Placement of bands, spectral response, gains/dynamic ranges, noise characterization, stability, and etc. (spec. compliance); Vigilance and knowledge
|  | Science team (with MCST) has to take on early post-launch assessment of instrument performance (strengths and weakness) and to help “tweak it” for scientific use |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Verify Scope | Product Validation | Vicarious calibration and science validation effort
|  | MCST effort needs to be sustained over the entire mission |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning | Track/correct sensor on-orbit changes, including optics degradation and changes in response versus scan angle (especially as instrument gets “older”); Communicate with science team (regular briefing via MsWG and calibration workshops during science team meetings); Coordinate with S/C operation team (for special activities, such as maneuvers and anomaly resolution)
|  | Interaction with contractor (challenges: role and funding over the entire mission |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Determine Budget | N/A
|  | Documentation and data records |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Management | Report Performance | Technical Data Management | Sensor test and characterization data, tools, and results (including pre-launch calibration and characterization); Progress report and instrument status update for community reference; Technical memos conference presentations, peer reviewed journals on topics of instrument operation and calibration, and lessons learned
|  | Mutual respect, integrity and trust are essential to a successful international collaboration |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Management | Manage Project Teams | N/A
|  | Importance of Communication |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Management | Plan Communications | Technical Planning | Regular Meetings; Teleconferences between meetings
|  | Lessons learned' are rarely used to good effect in future projects |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | N/A | Technical Planning | Part of the problem here is that 'lessons learned' are typically kept in the management, not engineering, domain
|  | 'Bad' decisions made early in a project tend to remain in place for the life of the mission |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Define Scope | Decision Analysis | Some design ideas are put into proposals without the benefit of time to look for 'better' approaches or designs. Such ideas should not be carried forward into the final design if better ones can be justified
|  | It is impossible to accurately estimate what a new (and non trivial) task will take in the way of time, but schedules are always of critical importance to a large project, and so schedules tend to be the tail that wags the dog |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Estimate Activity Durations | Technical Planning
|  | Important management metrics are typically schedule and cost. This is because cost is easy to quantify and track, and with suitable milestones, schedule can be tracked and reported |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Estimate Activity Durations | Technical Planning | One trouble with this is that milestones rarely map well into quantitative progress, especially for software and testing. For example, it is typically not recognized that writing software may be a shorter task than debugging it in a complex embedded environment. Similarly, assumptions are attached to test plans which simply cannot allow for the 'unknown' problems that often crop up. Adding people to a task rarely solves an underlying schedule problem, and can have the opposite effect
|  | The efficiency and quality of implementation of both hardware and software depends mostly on the 'quality' of the people doing the job, not on any schedule or work plan |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Acquire Project Team | N/A
|  | 'Heritage' designs are rarely a good match for a new instrument, and the necessary changes to make them a good match mean that they are no longer heritage designs |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | N/A | Product Implementation | It is usually best to start with a clean piece of paper after studying a heritage design
|  | Rules' based implementations usually make little sense and stifle innovation and out‐of‐the‐box thinking |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | N/A | Product Implementation | Any system of rules is merely documentation of what was done in the past, and that is only useful if doing exactly the same thing as before
|  | Interfaces and Team Size |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning | The larger a team on a particular task, the more interfaces there are between members of the team. The more teams are on the overall task, the more interfaces there are between teams. More interfaces means more documentation, more meetings/reviews, and more miss‐interpretation of documentation. The ideal team size is one person (all interfaces are with him/herself). The largest efficient team size is probably around three people. Beyond that, communication becomes a bottleneck. The interface/requirements issues are probably greater for software than hardware.
|  | Make early use of available resources (parts and reliability groups if available) to select electronic parts suitable for use in flight |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Sequence Activities | Technical Planning
|  | Experts' tend to have a some knowledge about a narrow field. Look for generalists – the good ones tend to know a lot about a wide range of subjects, and tend to be far more useful than experts. They also tend to be good mentors. |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Acquire Project Team | N/A
|  | Do not expect groups outside of your immediate domain to view sub‐tasks the same way as you view them ‐‐ they will typically see every task for a flight project as one with generous funding and needing lots of people. External groups do not necessarily have the same vision of time as you. |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | There is never enough time to perform all of the testing one would like |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Plan Quality | Product Verification
|  | Un-modeled ,Solid Earth tide (SET) effects can lead to significant errors in long-term Mean Local Time (MLT) prediction |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | N/A | Design Soluition Definition
|  | Inadvertent corruption of operational delivery area during simulation product transfer can negatively affect planned maneuver operations. |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Plan Risk Responses | Technical Risk Management
|  | Onboard Flight Software and FDS ground-based ephemerides comparison tolerances must be consistent. |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | N/A | Technical Requirements Definition
|  | Accidental “spillage” of classified data should be planned for |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Plan Risk Responses | Technical Risk Management
|  | Conjunction assessment process and ESMO management reaction to potential close approach event notification is still evolving |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Plan Risk Responses | Technical Risk Management
|  | The challenges associated with personnel turnover can be mitigated by developing a detailed training plan with hands-on mentoring |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Develop Human Resource Plan | Technical Planning
|  | All maneuverable spacecraft should have a retro-grade (orbit lowering) capability |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition
|  | Combination of Aqua and Terra: Enhanced many science products |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition
|  | Combination of Aqua and Terra: Captures diurnal variability |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition | Land Surface Temperature, Fire, Clouds, Aerosols
|  | Combination of Aqua and Terra: Increases opportunity for cloud free observations |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition | More opportunities for better viewing geometry (e.g. more near-nadir views); Ability to combine viewing geometries for BRDF/Albedo retrievals
|  | Combination of Aqua and Terra: Having Terra algorithms working well allowed for easier and earlier checkout of Aqua products |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition | Intercomparison made it easier to find anomalies
|  | Combination of Aqua and Terra: Aqua instrument characteristics made some products possible, e.g., Ocean Color, Deep Blue Aerosols |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition
|  | Overlapping missions (e.g., future TSIS and SORCE) are required until solar irradiance accuracies are improved to 100 ppm |  | ESMP | Aura | SORCE | [11 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition | Maintaining solar record gap risk to less than 5% over 30 years requires 5-year launch intervals; Glory TIM accuracy expected to be 100 ppm
|  | TDRSS 911 should be NASA standard capability |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Technical Requirements Definition
|  | Early Flight Operations Team involvement benefits S/C I&T and GS development processes |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Develop Human Resource Plan | Technical Planning
|  | Spacecraft Command Procedures benefit from early development of a Style Guide |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Sequence Activities | Technical Planning
|  | Daily Stored Command Load files (more is better than less) |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Developing procedures to operate the SSR can be challenging |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Estimate Activity Durations | Design Soluition Definition
|  | It can be challenging and time consuming to keep track of the multiple Check-summed Memory Loads (CMLs) which are required on the spacecraft. |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Estimate Activity Durations
|  | Develop configuration codes for all telemetry rates |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition
|  | Small on-board data storage capacity coupled with limited ground station sites created labor-intensive operations to capture all the data |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Reporting is crucial to long term missions |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Mature, complete and configuration managed procedures and processes are essential to successful mission operations |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Plan Communications | Configuration Management
|  | Provide the Flight Operations Team visibility into ground station equipment |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Plan Communications | Technical Planning
|  | Allow and encourage the Flight Operations Team to self-automate their processes and procedures |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | N/A | Product Implementation
|  | Require a plug-n-play database that the Flight Operations Team can maintain and deliver |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | A high-fidelity simulator is a must for mission success |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | The high-fidelity simulator should include a solid state recorder engineering model |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Dedicated orbit adjust thrusters |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Bit-Pack telemetry |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | Flight executive mission constant parameters tables |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition
|  | Over-reliance on “series redundancy” |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition
|  | During major operations (ie. Activation, Laser switch), having an engineer travel to the SOCC and act as a liaison provides a level of confidence and understanding in the communication between the teams. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Risk Responses | Technical Risk Management
|  | Regular face-to-face meetings are needed to resolve issues, complete documentation, and prepare for major reviews. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Communications | Technical Planning
|  | Discussions between the teams are must be open and candid. A level of trust between the teams is needed to allow for some speculation with regard to system performance and expectations. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Distribute Information | N/A
|  | Cultural differences should be understood and appreciated. If possible, the NASA team should learn the basics of the partner team’s language |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Communications | Technical Planning
|  | Design backup ground system capability to provide independent data paths, processors, and geographical regions. Plan for natural disasters and facility losses. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Risk Responses | Technical Risk Management
|  | Any automated ftp or email notification process should have a backup method for distributing information. During an anomaly missing data is often the first indication of a problem. The operators need an alternate data check to distinguish between ground and spacecraft errors. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Risk Responses | Technical Risk Management
|  | When constellations flying, your spacecraft operations have an impact on the entire constellation. Report to the constellation when you are planning to break normal configuration. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | N/A | Technical Risk Management
|  | Active space debris monitoring is necessary for missions in high risk orbits. This monitoring system is too complex and cost prohibitive for an individual mission to develop and maintain. The Goddard CA Team has been an outstanding resource. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Operations | Plan Risk Responses | Technical Risk Management
|  | Include a checksum on each telemetry frame. |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition | CloudSat uses convolutional encoding on engineering telemetry downlink. This encoding is stripped off at the AFSCN, so when data arrives at the project, we have no simple way to assess if the frame is “good”; This recommendation was also made by the SORCE flight team at their EOPM review. (Their Reed-Solomon encoding is stripped off at the GN, and they have the identical problem when the data arrives at LASP.)
|  | Plan extra processing capacity and data storage into your data processing facility. |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | For a team built from diverse organizations, don’t underestimate the time needed to network with those organizations |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Operations | Develop Project Team | Technical Planning
|  | Instrument operators should participate at the instrument development site during pre-delivery instrument testing |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Operations | Manage Project Teams | Technical Planning | The AIRS operations team was co-located with the AIRS instrument contractor for 18 months prior to delivery to the spacecraft contractor; Participated in all instrument-level testing and some assembly-level tests
|  | Instrument operators should be the same people, both pre‑launch and post-launch |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Operations | Manage Project Teams | Technical Planning | Two members of the original operations team are still on the Project (performing management and science support tasks); They are the developers of the command procedures; They have lived through all anomalies
|  | Automate routine operations to the maximum extent possible |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition | Minimizes human error; Permits lengthy activities in spite of short ground contacts
|  | I&T is to discover the unexpected/unwanted |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Perform Quality Assurance | Product Integration | FSW was not ready for I&T
|  | PFR closure |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Control Schedule | Technical Planning | With time crunch, some were closed too quickly, without thorough analysis all happened during early checkout
|  | S/W team not given enough guidance at the beginning |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Define Scope | Technical Requirements Definition
|  | S/W team used an architecture from deep space that may have been orthogonal to earth science |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition | Deep space is used to long delay after commanding, earth science is nearly immediate
|  | Hardware engineering needs to have software more integrated |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Define Scope | Logical Decomposition | Hardware thinks software can fix problems; software doesn't know how the hardware works
|  | Need upper level SE and mgr that understand technical issue to find an easy solution when Integration does not work (common sense) |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Acquire Project Team | N/A
|  | MLS was second generation, and 2nd generation can lead to complacency, complacency leads to problems and complacency does not dig deep enough |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Estimate Activity Durations | Product Implementation
|  | Need strong instrument scientist that understands the "intent" of the instrument not necessarily just the written requirements |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Acquire Project Team | Technical Planning | Cog‐E does not/may not understand; Written requirements cannot capture the instrument intent
|  | Project mgr needs to protect the team from over mgmt from external sources |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Manage Project Teams | N/A | Mgr needs to be honest
|  | Continuity of personnel ‐ Ops needs to be involved at I&T ‐ corporate knowledge |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Develop Human Resource Plan | Technical Planning
|  | Even the best specifications are not a design. Specifications need to be interpreted and converted into a design. |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition
|  | During software uploading, no return telemetry. Uploading takes a long time |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition
|  | Bring the software folks on board early and give plenty of guidance |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Acquire Project Team | Technical Planning | make sure they are part of the 'instrument team' in order to foster better communication between them and the hardware engineers (also reduces finger pointing)
|  | Don't toss the hardware over to the software engineers; hardware engineerss should write test software, document it, and provide it to the software engineers. |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | N/A | Product Integration | This forces the hardware engr to verify functionality and helps the software engr to under the hardware
|  | When inheriting equipment or software, don't assume it works as advertised |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Operations | Verify Scope | Product Implementation | keep an eye out for potential problems and test how you fly
|  | Automate difficult measurements & anything done twice |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Operations | N/A | Design Soluition Definition | You may end up doing them more than twice & less chance of mistakes
|  | Future missions should be designed with ample downlink margin in their ops concept |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Operations | Collect Requirements | Stakeholder Expectations Definition | Having the margin to downlink data more than once allows the ops team tremendous flexibility and allows creation of an extremely clean data set
|  | Do not always trust outside vendors to be experts at their craft, no matter what your prior experiences may have been |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Quality Assurance | Plan Procurements | N/A | Aura MLS mechanisms came in several years behind schedule, and one of the mechanisms (antenna scan) was so poorly implemented that it would probably have failed during the first few months of operation if it had not been modified and rebuilt by highly competent people at JPL. Mechanism control software development was a far more difficult and lengthy task than anticipated, even though the company in question had vast experience at this task. This arose because of a supposedly minor design change chosen to accommodate our request for low power consumption. If the company had talked to us more about this requirement, their design would have been more conventional, many problems would have been avoided, and much time saved
|  | Centralized QA activities for each discipline is invaluable |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Quality Assurance | Perform Quality Assurance | Product Verification
|  | Land group has the following functions: |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Quality Assurance | N/A | N/A | Global browse and golden tiles; Subsets and QA database; Known Product Issues web pages; Initial point of contact for user’s quality concerns; Help in tracking quality issues to source (sometimes in the upstream algorithm); Coordination and feedback on science algorithm testing
|  | Atmosphere team makes available: |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Quality Assurance | N/A | N/A | Projected granule browse of L1B and key atmosphere products; Images of hundreds of L3 global parameters including min, max, standard deviation fields; Collection highlights and known issues; Standard visualizations of all test data for the science teams
|  | Superwindow channel/SST validation and stability check invaluable |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Verify Scope | Product Validation
|  | AIRS Science and Validation Success Relies on Community Participation |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | Need stable instrument with uninterrupted operations for climate trending |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Define Scope | Technical Requirements Definition
|  | Journal publications are key to increased usage and buy-in from community |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | Transparency of algorithms, products, code, and QC is critical |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | Stakeholder Expectations Definition
|  | Simulation system was key to our readiness at launch and with each new version |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | N/A | Product Validation
|  | Algorithm must be robust to channel/instruments failure |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | N/A | Design Soluition Definition
|  | Cloud Clearing is fundamental to IR Remote Sensing |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Define Scope | Technical Requirements Definition
|  | Well supported validation program from NASA/NOAA essential |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Verify Scope | Product Validation | RaObs, Ship-based, Aircraft, ARM, etc.
|  | Cross-comparisons with instruments in A-Train and others invaluable |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | N/A | Product Validation | MODIS, TES, MLS, Cloudsat, ASTER, MISR, IASI, GOES
|  | Needed more effort in dedicated RaObs and RaObs at higher vertical resolution |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | N/A | N/A
|  | Products at Risk due to funding shortfalls |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Control Costs | N/A | UTH, Clouds, particularly over polar regions; Land Validation over land types (e.g. desert, forest, etc.); Trace gas products
|  | Validation is a continuous process |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | Verify Scope | Product Validation
|  | Subsetting the data and key instrument parameters is critical |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Science | N/A | Logical Decomposition
|  | Multiple 89 GHz horns minimized data loss when one failed (redundancy). |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Science | N/A | Logical Decomposition
|  | Scientists’ involvement during instrument design can help avoid problems. |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Science | Develop Human Resource Plan | Technical Assessment | Warm calibration load design required considerable work-around effort.
|  | Science integration at Team Leader Science Computing Facility (TLSCF) |  | ESMP | Aqua | AMSR-E | [11 empty] | Science | [5 empty] | Science | Plan Communications | Technical Planning | Co-location with SIPS led to faster resolution of anomalies, shared use of operational hardware and easier collaboration; Proposal did not anticipate the need for more TLSCF personnel which delayed algorithm readiness for delivering to SIPS
|  | NASA’s support of science teams is critical. CERES has core group doing instrument and algorithm work (mostly at LaRC). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | N/A
|  | CERES relies on science team (from academia and other government agencies) to: |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | Technical Assessment | Provide scientific oversight and external review; represent scientific community interests; participate in major decisions regarding CERES data products; perform data product validation (independent algorithms, surface-based measurements, etc.)
|  | Hold science team meetings where prime CERES data product users actually work (i.e., climate modeling centers like NCAR, GFDL, NASA GISS, UK Met Office, etc.). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Plan Communications | Technical Planning
|  | Develop easy-to-use subsets of data products in format that users want (e.g., netCDF). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Collect Requirements | Stakeholder Expectations Definition
|  | Dividing a complex data integration activity like CERES into working group structures is very effective. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Create WBS | Logical Decomposition | Each working group has a science lead, data management lead, and the group is responsible for algorithm, code development, validation, quality control, configuration management, etc., of their subsystems and data products; CERES data products are "owned" by individual working groups. A cross-cutting data management effort is used to handle broader software development issues like standards, interface control documents with other data centers, common code libraries used by many subsystems, configuration management, processing priorities, etc. CERES Working Groups: Instrument; Clouds; TOA Flux; SFC & ATM Flux; Time-Space Average
|  | Cannot underestimate the effort and resources required for data fusion (two or more instruments). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | N/A | Product Integration | Fusion of level-1 radiances (e.g., CERES, MODIS, Geostationary data) is the most complex.
|  | Data fusion at climate accuracy requires cross-calibration of instrument data being merged (e.g., GEO+MODIS; GEO+CERES). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | N/A | Product Integration
|  | Defining interfaces between subsystems early, completely, and with great care makes it faster and easier to develop code in parallel. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Create WBS | Interface Management
|  | Develop and test algorithms on the same kind of platform and computing environment as is used in production at data center. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Verify Scope | Product Validation
|  | Switching from one operating platform to another cannot be done overnight. Must allow substantial overlap between platforms. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Estimate Activity Durations | Configuration Management
|  | System-wide changes, such as OS upgrades and changes to standard directory structures, require a significantly longer time to implement and coordinate than originally thought |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Estimate Activity Durations | Configuration Management
|  | Once algorithms have been developed, majority of time is spent on exception handling, particularly validation of ancillary input (e.g., geo calibration). |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Estimate Activity Durations | Product Validation | For climate quality, the number of lines of validation code is a factor of 2 greater than production code.
|  | Data Quality Summaries (DQS) are useful tool for communication with users. |  | ESMP | Aqua | CERES | [11 empty] | Science | [5 empty] | Science | Distribute Information | N/A | Include data product accuracy tables, cautions and helpful hints. Users required to read before ordering product. Living documents that can be updated as questions arise and problems are found.
|  | Scientific events (e.g. volcano eruptions) can push science collaboration |  | ESMP | Aura | OMI | [11 empty] | Science | [5 empty] | Science | Plan Risk Responses | Technical Risk Management
|  | Level 1 requirements should be clearly and concisely defined, expressed in terms of quantities that map well to the underlying uncertainties, and verifiable |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Collect Requirements | Technical Requirements Definition
|  | Algorithm development and tuning is a very time consuming activity. The level of effort needed is easily underestimated (even after years of experience) |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Estimate Activity Durations | Product Implementation
|  | In many cases, the effort needed scales faster than linearly with the number of products |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Estimate Activity Durations | Product Implementation | There are many complex interdependencies in the MLS measurement system (typical for composition instruments)
|  | Get file formats defined and data management / inspection tools in place as soon as possible (ideally a few years before launch) |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Control Scope | Configuration Management | They need to become second nature, in order to allow the team to concentrate on algorithms and science
|  | Assign responsibility for inspection of each product (including the diagnostics) to specific team members |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Manage Project Teams | Logical Decomposition
|  | Pre‐launch testing of end‐to‐end processing and data inspection is essential |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Verify Scope | Product Validation | Once the data fire hose turns on, it is much harder to catch up if tools are not in place and very familiar to all
|  | Having a clear, well structured data quality document / users guide allows interactions with users to be focused on science and detailed product issues, rather than endlessly being in ‘help desk’ mode |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | N/A | Design Soluition Definition
|  | Getting reliable data out early to the community wins many friends, gets external scientists interested early on, and helps assure management that the team is in good shape |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Science | Manage Stakeholder Expectations | N/A | ‘warts and all’ is fine, users may identify issues the team hasn’t spotted yet
|  | The value of the 29-year long TSI data record increases with length and is lost if discontinuous, making gap avoidance critical; |  | ESMP | Aura | TIM | [11 empty] | Science | [5 empty] | Science | Develop Schedule | Stakeholder Expectations Definition | Because of the value of the long TSI record in determining climate sensitivity to solar forcing, should maintain TSI data continuity with 95% probability for at least 30 years
|  | Maintaining TSI data record continuity at 95% for 30 years requires 5-year launch intervals |  | ESMP | Aura | TIM | [11 empty] | Science | [5 empty] | Science | Develop Schedule | Technical Requirements Definition
|  | Overlapping missions are essential to building a reliable long-term record. |  | ESMP | Aura | SOLSTICE | [11 empty] | Science | [5 empty] | Science | Develop Schedule | Technical Requirements Definition
|  | Defining software functionality to the level needed to allow a team to go away and write the embedded software for an instrument is next to impossible |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Software Development | N/A | Design Soluition Definition
|  | Review the software team's progress early and often in order to determine where 'requirements' are incomplete or have been misinterpreted |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Software Development | Verify Scope | Technical Assessment
|  | For a non‐trivial instrument, expect software to arrive buggy and late |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Software Development | Estimate Activity Durations | Technical Planning
|  | Embedded software can only make efficient use of hardware if the writer fully understands that underlying hardware. If that is not the case, the software typically looks much like analysis software, which is usually far from optimal for a real‐time embedded system. |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Software Development | N/A | Design Soluition Definition | Ideally the hardware designer(s) and software writer(s) for that hardware should be the same person
|  | EOS Fault Management implementation was a success because of a dedicated Fault Management Working Group |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Software Development | Plan Risk Responses | Technical Risk Management
|  | The post-launch flight software cognizant engineer should participate in the flight software development at as early a stage as possible |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Software Development | Develop Human Resource Plan | N/A | The AIRS flight software cognizant engineer was co‑located at the instrument contractor’s facility part-time and was co‑developer of the code
|  | A modern integrated development environment is a must for developing the flight software |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Software Development | N/A | Logical Decomposition | The AIRS processor was poorly supported (compilers, debuggers, etc.)
|  | Flight software needs to be flexible and patchable—no hard-wired operational modes! |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Software Development | Define Scope | Technical Requirements Definition | AIRS meets this requirement; AMSU-A and HSB do not
|  | ST members should play a key role in development and maintenance of code – remain responsible |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Software Development | Develop Human Resource Plan | Technical Planning | It is better to produce some experimental products at the Scientist Team Member’s Computing Facility – but a method is needed for eventually bringing code into the primary production facility
|  | Science team led processing is needed to ensure that the best products are generated and reprocessed with a workable schedule |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Software Development | Develop Schedule | Technical Planning
|  | Product Delivery Preparation: Coordinate with ASDC on new ESDT definitions and potential data volume increases |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Close Project or Phase | Product Transition
|  | Product Delivery Preparation: Provide preliminary examples of new products to DAAC personnel for ingest testing |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Close Project or Phase | Product Transition
|  | Product Delivery Preparation: Adherence to Aura guidelines has made the development of combined EOS instrument data products easier to design and coordinate |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | N/A | Configuration Management
|  | New release operations preparation: Define and delivey software PGE Specification documents as early in the development cycle as possible to allow SIPS time to update production rules or database schema |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Define Scope | Technical Requirements Definition
|  | New release operations preparation: Define and verify that the development/testing environment and SIPS OPS environment are the same. Small differences in node CPUs and operating systems need to be taken into consideration |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Verify Scope | Product Verification
|  | Validation dataset definition: Prepare and deliver a listing of a comprehensive validation dataset to be run when a new software release is made available to SIPS for testing. This may contain up to a year’s worth of data to test all of the species and collection schemes from TES. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Verify Scope | Product Validation
|  | Validation dataset definition: Identify a subset of the validation dataset to check algorithm and support products file correctness. Re-running the entire validation dataset with a modified ABSCO version resulted in a significant delay of the Version 5 (R12) software delivery. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Verify Scope | Product Validation
|  | Reliance on our customized software testing environment requires more attention spent on maintenance to keep it current with changes to our PGEs. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Plan Quality | Product Verification
|  | Modification to our calibration scheme necessitated a large time investment to upgrade CASPER to handle multiple data collection scenarios. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Estimate Activity Durations | Design Soluition Definition
|  | Level 2 separation of the retrieval algorithm and a strategy table to control the processing steps/dependencies between species retrievals has proved invaluable |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Create WBS | Logical Decomposition
|  | Use of Rational Rose (UML design tool) has made algorithm updates straightforward and the object-oriented design allowed for “big picture” view on repercussions of small and large updates to the L2 algorithm |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | N/A | Design Soluition Definition
|  | Easily modifiable parameters (i.e. – first guess quantities, a priori for each quantity, forward model values,…) in the strategy table have eased development/updates to the processing sequence of stages, inputs and outputs for the L2 retrieval algorithm. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | N/A | Design Soluition Definition
|  | Addition of new species has been relatively easy with the determination of where to perform the retrieval step in the Level 2 dataflow. The separation of algorithm and strategy tables allows for easy prototyping and algorithm development. |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | N/A | Design Soluition Definition
|  | Allocating a significant period of time (up to three months) for science team validation of initial results from a software delivery has helped greatly in the quality of the products delivered to ASDC DAAC |  | ESMP | Aura | TES | [11 empty] | Science | [5 empty] | Software Development | Estimate Activity Durations | Technical Planning
|  | Near Real Time (NRT) data system is needed for application users (MODIS Rapid Response experience) |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | Collect Requirements | Stakeholder Expectations Definition
|  | Stand alone NRT system is needed to avoid gearing the entire production stream to the NRT constraints |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | Collect Requirements | Technical Requirements Definition
|  | Should be developed once the instrument has stabilized and data products are at Stage 1 Validation |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | Sequence Activities | Technical Planning
|  | Direct Broadcast (DB) versions of code make it easier for broad product uptake and use – increases standardization |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | N/A | Design Soluition Definition
|  | DB encourages applications and regional algorithm development and has been a huge success with > 100 direct readout sites worldwide |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | N/A | N/A
|  | Some products originally developed by application users (e.g. Polar Winds) could be considered as future standard products |  | ESMP | Aqua | MODIS | [11 empty] | Science | [5 empty] | Stakeholder Expectations | N/A | Product Transition
|  | The excellent performance exhibited by the CALIPSO LIDAR indicates that there are many things that were done right in the development of the instrument. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | Leveraged previous experience (Many lessons learned from LITE and other earlier instruments were taken into account in the design of CALIPSO. Many of the people involved in CALIPSO had previously worked on LITE.) Iterative development of requirements (The science requirements, the instrument requirements and the instrument design were developed iteratively, with the aid of fairly detailed instrument simulations). Continued attention to detail (There was continuing interaction between the project team and the prime payload contractor team to ensure that critical design details were being dealt with appropriately.) Good use of on-board processing (Extensive on-board processing was used to minimize the data rate and to provide condensed science data in the status data for performance evaluation and trouble shooting. Autonomous range gate changes, based upon GPS data, were critical to the seamless operation of the instrument.) Simple design (Simple laser requirements almost certainly contributed to its long life. Autonomous operations were used sparingly. No autonomous adjustments to the laser or receiver gains etc. No complex autonomous recovery from faults.)
|  | The SNR measurements pointed out two areas where the performance was not as good as had been anticipated |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Instrument | N/A | Design Soluition Definition | Detector noise in the SAA (Would have leaned more toward photon counting or hybrid photon counting/analog detector electronics if we had fully understood the extent of the potential problem.) Daytime misalignment: A boresight (quad) detector would have allowed better characterization and compensation for the problem. (A quad detector had been in the original design, but was eliminated for cost reasons.) A more thermally stable design for the boresight adjustment mechanism might be possible (A different method of boresight adjustment [e.g optical within the receiver]. No boresight adjustment mechanism [was thought to be too risky].)
|  | The CALIPSO team has developed an excellent working relationship with their international partner, CNES, supported by excellent communications throughout the team. This working relationship has developed because of two factors. The successful communications has developed because of frequent face-to-face meetings that have built trust, understanding and respect for the cultural differences. In addition, the inclusion of CNES’s REVEX in the CALIPSO review process has been extremely helpful in enhancing the communication and collaboration between the science and engineering communities across international lines. |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Develop Project Team | N/A
|  | The CALIPSO Mission Operations Manager has acted as a liaison for the CALIPSO international partner, CNES, not only for CALIPSO but also for the PARASOL mission. This has proven useful in ensuring that everyone is completely informed on what is going on in the constellation and what needs to be done and reported. A prime example of this communication need concerns conjunction assessments. For CALIPSO, GSFC is responsible for conjunction assessment but this Air Force sensitive data must be communicated to a foreign partner who is responsible for maneuvering the CALIPSO spacecraft. The mission operations manager acting as a liaison between NASA and CNES ensures this process is smooth, that appropriate data is passed to a foreign partner and all information is completely understood. It is recommended that all future missions with foreign partners flying in constellations have an identified NASA liaison (e.g. GCOM-W1). |  | ESSP | CALIPSO | [12 empty] | Science | [5 empty] | Management | Acquire Project Team | N/A
|  | EOS Aqua flies in the Afternoon Constellation (A-Train) of Earth Science satellites. A number of observations and/or lessons learned have been repeatedly mentioned during the development and population of the A-Train |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Design Soluition Definition | Contributions to Earth Science by the whole Afternoon Constellation exceeds the sum of the individual mission contributions. Building “Virtual Science Platforms” in pieces rather than large “Observatory-Class” missions offers a lower overall cost solution with greater flexibility. A single launch failure will not wipe out the entire observing program.
|  | Multi-mission flight operations is a proven approach to providing cost-effective mission operations. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Design Soluition Definition | Multi-mission Flight Operations Team (FOT) – Terra, Aqua & Aura (Shared multi-mission management team, Shared multi-mission planning and scheduling team, Shared database maintenance and configuration management). Common spacecraft bus for EOS Aqua and EOS Aura (On-line team operates Aqua & Aura as a single satellite, Off-line engineering team share select subsystem engineers). EOS Aqua benefits from cost-effective, multi-mission operations that take advantage of the economy-of-scale of operating three missions with two nearly identical spacecraft buses.
|  | Aqua, Terra and Aura, benefit from multi-mission ground systems that operate the EOS missions and provide services to other NASA missions for level 0 data processing and conjunction assessment |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Design Soluition Definition | Multi-mission EOS Operations Center (EOC), Multi-mission EOS Data Operations System (EDOS), Multi-mission Flight Dynamics System (FDS), Multi-mission Constellation Coordination System (CCS), Multi-mission Conjunction Assessment System (CAS)
|  | Sharing ground systems drives satellite phasing |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Design Soluition Definition | Aqua passes same polar regions as Terra approx. 20-minutes later. Phasing was established to minimize contention for limited ground station resources. Initial EOS Aura orbital location was selected to minimize contention for limited ground station resources, and to allow the EOS Aura MLS instrument limb observations to view the same air-mass EOS Aqua had observed approximately 8-minutes earlier.
|  | Resource sharing enables the sharing of computer systems & networks, ground systems developers, system administrators, and software licenses. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Define Scope | Design Soluition Definition | Systems need to be continuously evaluated and updated to mitigate the increasing IT security threats and to adhere to NASA IT security policies.
|  | Long-duration, Multi-instrument, Multi-Center, International missions are complex to operate and require more resources than short-duration, single-instrument missions |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Requirements | Estimate Activity Resources | Technical Requirements Definition
|  | Minimizing the number of maneuvers is challenging. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Requirements | Collect Requirements | Technical Requirements Definition | Aqua SORD Requirement: The orbital maneuver planning shall utilize passive inclination and mean local time control to minimize propellant usage. Aqua SORD Requirement: The orbit period (SMA) shall be maintained such that the time between maneuvers is maximized
|  | Orbital safety aspects of flying missions in close proximity to each other and avoiding orbital debris should drive the design and capabilities of spacecraft subsystems. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Requirements | Collect Requirements | Technical Requirements Definition | Propulsion Subsystem (Number, size and location of thrusters, Dedicated thrusters for delta-v maneuvers, Dedicated thrusters for attitude control maneuvers). Guidance, Navigation & Control (GN&C) (Reaction Wheel size and slew capabilities, Mission should have the capability of performing retro-grade delta-v maneuvers (orbit lowering) during the routine mission operations phase of the mission. Not just during end-of-mission decommissioning when the instruments are no longer collecting science data.)
|  | Constellations and the ground systems that are necessary to safely fly them (e.g. ESMO’s Constellation Coordination System (CCS) should be recognized as line-items in the budget process. System (CCS) and Conjunction Assessment |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Requirements | Estimate Activity Resources | Technical Requirements Definition
|  | The EOS Aqua mission had no Constellation-flying requirement pre-launch |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Requirements | Control Scope | Requirements Management
|  | EOS Aqua Inclination Adjust Maneuvers (IAMs) are highly-constrained |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | N/A | N/A | All burns must be completed while in spacecraft night. 12 minute yaw before and after each burn on thrusters. Maneuver near equinoxes (maximum burn duration & efficiency). Multiple 10-minute burns required, centered at Descending Node. Allow 2 days between burns for ease of operations
|  | Performing the minimum number of maneuvers is not always possible or operationally desired |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | N/A | N/A
|  | Simple quadratic relative motion model based on relative position at the equator once per day has worked well for formation maneuver planning. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | N/A | N/A | Used longer than anticipated interval (16 days) in the estimate of relative acceleration to eliminate short term variations. Propagators with high fidelity gravity and atmospheric models were not required, but were used as cross checks. Maneuver errors more of a problem on drag makeup maneuvers because they are so much larger than formation flying maneuvers.
|  | Maneuver planning driven by programmatic issues as much as orbit dynamics |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | N/A | N/A | Black-out periods for science campaigns, MOWGs, and holidays. Requires looking beyond next maneuver and adjusting maneuver size to control timing of following maneuvers. Early warnings help
|  | Perform all expected maneuver types (orbit and attitude) during the launch and early orbit (LEO) in orbit checkout (IOC) phase of the mission |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | N/A | N/A
|  | Test as you will fly, fly as you tested |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Verify Scope | Product Verification
|  | Developing the plans and procedures after the fact consumes a significant amount of resources that take away from routine operations of the mission |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Mission planning | Estimate Activity Resources | Technical Planning
|  | Full-up engineering team is available to execute the maneuvers that should have been simulated and rehearsed during pre-launch integration and test |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Operations | N/A | N/A
|  | Flying in a constellation requires additional time and effort on the parts of the operations teams to ensure mission and constellation orbital safety. |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Operations | N/A | N/A
|  | Collision Avoidance Capability Maturial |  | ESMP | A-Train | [12 empty] | Science | [5 empty] | Operations | N/A | N/A | Threat of on-orbit collision with orbital debris is real; A risk to one is a risk to all; First NASA mission to screen ascent burns; Leader in development of close approach avoidance between member mission of the Afternoon Constellation; Leader in development of operational collision avoidance for orbital debris; First mission to perform routine Conjunction Assessments; EOS Terra 1st NASA Robotic Mission to perform a debris avoidance maneuver; EOS Aqua experience led to other member missions of the Afternoon Constellation developing their own technical approach to operational collision avoidance
|  | Procure, assemble, and install flight battery as late as possible in the development phase |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Integration and Test | Plan Procurements | Product Integration | Unless absolutely necessary use a test battery for I&T; Battery would not have been a concern if it had been procured and installed less than a year from launch
|  | Incorpoate Gyroscopic or Intertial Reference Units |  | ESSP | CloudSat | [12 empty] | Science | [5 empty] | Hardware Development | Plan Procurements | Design Soluition Definition | Issue with glint off earth in sun sensors wouldn’t have occurred Spacecraft maneuvers would be simpler in planning and execution Wouldn’t have had to modify FSW fault protection prior to launch to protect against loss of star trackers; Wouldn’t have had to develop new tools at RSC for modeling star tracker outages; Star catalog precessions (2 per year) would be simpler in execution; Double star tracker outages would not be an issue
|  | The challenges associated with protecting spacecraft from increasingly sophisticated hacker tools are increasing. |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Technical Requirements Definition | Since launch there has been a significant increase in the number of sensitive NASA systems that have be been compromised; The sophistication and availability of the hacker tools is increasing; The hackers frequently operate in well-organized teams; The Internet provides the hackers access to our systems from anywhere in the world; All future NASA missions will have to design their systems from the ground up with IT security and maintainability in mind and budget for routine IT security assessments and upgrades; All future missions will need to address Space Asset Protection.
|  | Using a common multi-mission Level Zero Processing System reduces costs |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition | One system to maintain and to keep updated to increasing IT security requirements; All benefit from a robust architecture and each new enhancement; Autonomous Data-driven architecture reduces costs and eliminates complex scheduling requirements; Evolutionary Design cost effectively adapting to new missions (Support of data rates up to 500 Mbps. Processed ALOS “IF” stream at 288Mbps with Zero data loss; Flexible design with IF interface and programmable front-end (FPGA based) architecture and IF interface simplifies addition of future requirements.); Proven architecture supports receipt of data at multiple ground stations optimizing the use of expensive data circuits through data prioritization (Currently delivering over ½ Terabyte of data each day); Provides secure external interface allowing customers real-time access to data status.
|  | Concerns with interference while Terra overflying DSN stations | Direct broadcast: proper filters on Aqua worked out well (Lesson Learned from Terra) | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition
|  | Direct Broadcast transmission has to be shut down to playback SSR | Design a system capable of Direct Broadcast & Playback simultaneously (NPP appears to have resolved this Aqua limitation); A modern recorder should have the ability to send null files to achieve lock-up. A modern recorder should support a file structure and file transfer. EOS-Aqua does this. | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition
|  | Design Ground Science Equipment for the spacecraft. Ground system Science equipment designed based on Terra (which does not have preamble), and assumes data overlap. Ground System Science Equipment took a shortcut, and drops CADUs based on a contact, and does not piece back together contact-to-contact. | Have developers use documentation and not assume requirements based on other spacecraft. | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition
|  | Multiple ground data systems waste resources and endanger the hardware |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition | Four different systems had to be learned and used: the instrument contractor’s system; FOS (aborted EOS-funded system canceled before launch); Epoch (used at the spacecraft contractor for I&T); EMOS (includes Eclipse) used today at the EOC.
|  | Instrument operations teams should be able to test command procedures and telemetry decommutation and displays using a local copy of the ground system software at their home institution |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition | Epoch allowed this and it allowed us to meet schedule; EMOS Eclipse segment did not
|  | A flexible and easy-to-use instrument health and science telemetry monitoring tool must exist |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Design Soluition Definition | Must handle both high time resolution plots and entire mission plots with equal convenience; Must be modifiable by the instrument teams
|  | NASA (or some other government agency) must plan for and support data record storage and access for an indefinitely long time |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Data Processing | Collect Requirements | Technical Requirements Definition | Need permanently maintained non-proprietary software which uses open data formats to ensure that all data records are readable for the indefinite future; Need to require and support the use of long-lived media and provide the necessary storage facilities and data access capability
|  | Careful delivery planning and execution for science software development |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Software Development | Collect Requirements | Technical Requirements Definition | Early-on – develop ICDs and Operating agreements. Delivery Planning – coordinate with each user agency (GES DISC (GSFC DAAC) – standard products through Level 3, NOAA – primarily radiance products – BUFR format by NOAA, Direct Broadcast – modified standard products through Level 2). Staged Delivery Releases – ensures quality at all levels: (Lead delivery to GES DISC – verify PGE and product data flow first, NOAA distribution after GES DISC is running with current release. Direct Broadcast release follows once GES DISC and NOAA are operational). Verify all data products before formal announcement and release (The AIRS Project has never experienced a failed release, Even after release, frequent data product checks performed).
|  | Team Software Development |  | ESMP | Aqua | AIRS | [11 empty] | Science | [5 empty] | Software Development | Collect Requirements | Technical Requirements Definition | Issues: (Resultant code is overly complex, is not optimized, is coded in multiple languages, and includes too much shared common; Complex inter-dependency loops exist between L2 module developers; Not all Science Team members are familiar with update code base in a configuration managed environment). Benefits: (Ability of Science Team to closely interact and update the actual retrieval code; Development of a better retrieval algorithm; Science Team remains deeply engaged in the process)
|  | In a multiple instrument suite, all instruments should have the same design lifetime, same quality of calibration, and same level of quality control during manufacture |  | ESMP | Aqua | [12 empty] | Science | [5 empty] | Instrument | Plan Quality | Product Verification | AMSU-A is degraded and HSB has failed while AIRS remains healthy
|  | Maintaining a climate data record with the accuracy and complexity of CERES is a challenge within the NASA organizational structure |  | ESMP |  | CERES | [11 empty] | Science | [5 empty] | Data Processing | N/A | Product Transition | NASA mindset of only doing something once and then moving on makes it a constant struggle to maintain the CERES CDR effort; NASA needs to build a culture for part of its effort to assume that CDRs will exist within the NASA organizational structure; Cost of creating CDR with high level of data fusion is poorly understood (not simply proportional to instrument mass and data rate...); Continuing a CDR requires a ‘cradle-to-grave’ approach. The science team must have responsibility for the entire program lifecycle: instrument design, fabrication, assembly, test, spacecraft integration, post-launch instrument operational tasking, data processing and validation; While individual instruments are tied to specific missions (CERES_Terra, CERES_Aqua, CERES_NPP, etc.), the CDR science team works seamlessly across all missions. Nevertheless, current CDR science team budgets and reviews are structured around missions. A single CDR science team budget across all missions and periodic peer-reviews of the CDR science team is a far more natural structure. Current Senior Reviews every two years for each mission CERES flies on results in a 15% loss of efficiency for project leadership.
|  | There is no straightforward way to transition CDRs like CERES (complex from data fusion, but at climate accuracy) from NASA to NOAA. |  | ESMP |  | CERES | [11 empty] | Science | [5 empty] | Data Processing | N/A | Product Transition | The decades of expertise used to validate, understand, quality control, and continuously fix input data sets cannot be bought or transplanted as a set of documents and software. CDRs are inherently more research data products than they are operational data products.
|  | Have clear (and shared) science objectives |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Science | Collect Requirements | Technical Requirements Definition | HIRRLS (proposed by NCAR) and DLS (proposed by the University of Oxford) both had clear, well articulated science objectives; Their similarity made it easy to combine efforts in HIRDLS; This also made writing the Science Requirements Document (SRD) straightforward; These objectives have not changed over the life of the experiment; These two organizations, later including the University of Colorado, could proceed enthusiastically to achieve these goals
|  | Science team involvement from “cradle to grave” is crucial |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Science | Collect Requirements | Technical Requirements Definition | Early writing of Instrument Requirements Document (IRD), to achieve goals of SRD (Having a prototype retrieval algorithm critical to getting quantitatively correct requirements; Previous experience is a huge advantage). Science Team involvement in: (Instrument design, fabrication, assembly, testing, calibration, S/C integration, post-launch operations and data processing, data validation, and scientific application of the data )
|  | No single point of failure |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Instrument | Plan Quality | Design Soluition Definition | Gyro 0 bias saturated – not mission critical, since there are four gyros on HIRDLS and any three are adequate to give us the information needed. Chopper stalled – mission critical, since this single point of failure caused HIRDLS to stop taking science data. Should provide adequate funding to perform life test on multiple units, and adequate time to complete life test prior to flight.
|  | Get innovative for best possible pre-launch calibration |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation | Design cryogenic instruments to allow them to be operated in ambient conditions for testing; Develop integrated facility with multiple calibration sources and reduce risk by verifying procedures with the EM instrument so that risk due to schedule compression can be mitigated. As a general rule - don’t cut pre-launch calibration time - the better you know your instrument the more chance you have of dealing with problems after launch; Early very detailed planning, based on the IRD, and investment are crucial to a successful detailed calibration in a vacuum; Remote operation is crucial to rapid and efficient calibration; Take and save all data - you never know when it will be necessary.
|  | Take the time and effort to ensure calibration stability and traceability. Strong heritage from ISAMS at Oxford |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation | Innovative external black-body targets met specification with margin: identical pair; full temperature range; high emissivity; incorporated secondary national standard temperature sensors. Innovative combined monochromator/collimator included polarizers and wavelength calibration -> Spectral dependent spatial response. Extensive screening and selection of temperature sensors from large batch gave reliable calibration stability. Variable temperature space-view target for offset sensitivity (helped after launch!).
|  | Know your calibration equipment and facility. Be prepared for quick turn-around of results and flexible operations. |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation | Vibration isolation of HIRDLS from equipment and facility; Pre-canned computer based building-block scripts for more reliable & flexible ops; Capability to discriminate out of field response to 10-8 level; Sufficient staff with appropriate skill sets for 24/7 ops – to fix problems any time; Understanding your calibration equipment is a prerequisite to knowing your HIRDLS.
|  | The material (kapton) used for contamination close-out in the optical cavity ripped during launch and a piece of it ended up in front of the scan mirror, blocking the majority of the aperture. | The launch environment of rapid decompression should be included as a key component of the ATP. | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Integration and Test | Plan Quality | Product Validation
|  | HIRDLS Kapton anomaly pushed the limits of the data production system. |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Data Processing | Plan Quality | Product Validation | Our production system became an experimental test bed; We ran tests on more than 300 combinations of processing modules; Detailed metadata and records of data provenance organized what could have been chaotic; Co-locate science, software development and production teams; The close teamwork was invaluable for our constant experimentation; Quick turnaround of processing experiments; Quick resolution of integration problems; Quick feedback on requirements from science users to SIPS development and operations staff.
|  | Asset sharing and fully utilize technological capability – may be more effort up front but pays dividends after launch. |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Operations | Develop Human Resource Plan | Technical Planning | On-board programming language 'SAIL' permitted very flexible operational routines – particularly for scanner motion, optical thermal control, focal plane thermal control and later for chopper restarting. Was designed by John Barnett (strong ISAMS legacy), implemented by Lockheed. Tremendous asset; Utilized during pre-launch calibration (helped efficiency); Expertise concentrated with a few people – may have helped to train more people; Operations personnel included people from instrument development, I&T and continued through mission => very knowledgeable; Asset sharing ops lead between Oxford and Colorado – benefitted as staff loss occurred and extended the effective working day (8 time zones).
|  | Investment in rapid dissemination of flight data (RBD) provides powerful on-orbit insight. |  | ESMP | Aqua | HIRDLS | [11 empty] | Science | [5 empty] | Operations | Collect Requirements | Technical Requirements Definition | Practice sessions at GSFC very valuable (MT, SCIF, DITL); Excellent asset with short (90 minute) latency for rate buffered data (RBD & DMP) at the IOTs, together with bespoke trending and limit checking software gave comprehensive insight into instrument performance; Tremendous support from FoT at the EOC – has helped in all aspects of ops and anomaly work – superb team, ground systems and spacecraft.
|  | Integration and Test Information |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Integration and Test | N/A | N/A | Schedule management: ‘hurry up and wait’ (Project management ‘hoarded’ schedule margin which put intense pressure on the team during I&T at Redondo Beach, and resulted in useless margin after arrival at VAFB); No monitoring of Survival Bus voltage/current (Temperature monitoring will have to do.); There had been an issue flagged at the MLS Instrument Pre-Ship Review: (Writing Discrepancy Reports [DRs = vendor equivalent of a JPL P/FR], Software Change Orders, etc is NOT familiar to JPLers, leading to inefficiency; These items were eventually resolved, although the NGST guidelines continued to change over time; Example: by the end of spacecraft activities, vendor QA insisted MLS log every high-bay activity in their procedure, including simple ones like turning on air conditioners.); Instrument teams need to be flexible; Continually changing plans at the observatory-level demanded adaptation by all parties involved (added twist: spacecraft contract was with GSFC, and they were not obliged to check with instrumenters on their contractual assumptions for planning the Observatory I&T effort [i.e., instruments were at the beck & call of the S/C when events changed]; the Instrument Providers were under separate contracts (or working agreements) with GSFC; because of the GSFC organizational structure, this ‘gap’ was never resolved, and put tremendous pressure on the Instrument teams); Certain accommodations were made to support the remote activities (Observatory Comprehensive Performance Tests (CPTs) were 24/7: Project office processed an administrative waiver (spacecraft site < 50 miles from JPL) so that team members could stay at a nearby hotel; During Observatory TV, shift starts were staggered to avoid high-traffic times on LA freeways); Know your requirements (Again, this will help when determining what to do when observatory plans change)
|  | Good System engineers learn from broad experience. System engineering classes provide the framework, but not the experience. Having a good system engineer (even if he has a different title) is essential |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Acquire Project Team | Technical Planning | Proper system engineering requires someone who understands all aspects of the instrument: science goals, physics behind the measurements, instrument calibration, and has in‐depth electronic and software experience, etc; Science requirements do not flow down directly to a good instrument design unless there is a true system engineer to interpret the requirements. Even then this is a very difficult task; Ideally the system engineer should also be responsible for some important aspect of the instrument implementation task (e.g. calibration, performance verification, ...); If you cannot find an ideal system engineer, then find a suitable Instrument Scientist (or someone with a similar title) who understands the goals, measurements, physics, and hopefully has appropriate hardware and software experience. One can then use the Instrument Scientist to perform the true system engineering, and the System Engineer to handle the other aspects of the task (documentation, reviews, reporting, ...). This kind of team worked fairly well for MLS
|  | For MLS, having an Instrument Manager with excellent 'people' skills, instrument design experience, a good knowledge of physics, and the belief that is was his job to address problems promptly, pragmatically and efficiently, was a tremendous asset |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Acquire Project Team | Technical Planning
|  | An organization may have a management‐mandated idea of how to assign responsibilities which does not always make the most sense, but is 'the way things are done.’ |  | ESMP | Aura | MLS | [11 empty] | Science | [5 empty] | Management | Develop Human Resource Plan | Technical Planning | For example, the Aura MLS responsibilities were assigned 'vertically,' by which I mean that 'detectors' were one responsibility, the following amplifiers/signal chains belonged to someone else, the signal analysis electronics to yet another person; This resulted in no individual being responsible for any particular end‐to‐end signal chain, and created the need for documents defining the interfaces between these individuals, with the tendency for interfaces to be overdefined. When changes were needed, instead of an individual making an appropriate change or trade‐off, there arose the need for presentations, meetings, and management involvement.
AO SOW | AO Selection | Make sure that it is clear in the AO that a “good” SOW (including expected deliverables) is available to start working on contract negotiations. Delays in providing this to the Program Office will delay getting under contract | SOW should include attributes. An expectation should be set that it will take 10-12 weeks to start, define selection vs. ATP. Place an example/template in the library. | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Management | Estimate Activity Resources | Technical Planning
SOW Start Date | AO Selection | AO should be clear that Start Date for the winning proposal should be XXX days/months after winner is announced. (3 ½ months from having a “good” SOW is typical for missions that do not have a NASA center involved. It could take weeks/months to develop a “good SOW” if it is not included with the Proposal | Ensure start date is defined | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Management | Estimate Activity Resources | Technical Planning
AO MAR | AO Selection | Mission Assurance Requirement (MAR) should be clearly identified in AO | Put example MARs in AO/ESSP library | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Requirements | Estimate Activity Resources | Technical Requirements Definition | The MAR requires a lot of resources, this should be explained during the announcement so expectations can be met.
AO Requirements | AO Selection | 7120.5D -81 or better was specified in AO. However, -81 was already dead by many months when the AO went out and -97 was in effect (which added a lot of requirements). Rev E was signed while we were in the middle of contract development | Try to stay abreast of what requriements are in revision | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Requirements | Collect Requirements | Technical Requirements Definition
AO Interactions | AO Selection | Need to improve SOMA and PO Interactions | SOMA should provide the ESSP PO with the Form C results from the TMC evaluation. This should be done days/weeks in advance; Should allow the “full” (ie NASA civil servant and contractors) ESSP PO team should be allowed to hear the SOMA debrief; SOMA charts should be printed in color or/and the charts that SOMA presents should be marked in such a way that color within the charts does not matter | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Management | Define Scope | Technical Requirements Definition
Program Team | AO Selection | The team is weak in software; Had to go outside the team to get assistance, were challenged getting assistance | Key is to have contracting and SMA in the room while creating the SOW Get help in Software, Contamination Control, EEE Parts to review data from the Contractor in Phases A-D | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Quality Assurance | Perform Quality Assurance | ?
FAR Waiver | AO Selection | Waiver is needed if project is longer than 5 years |  | ESSP | CYGNSS |  | 2012-08-28 | [10 empty] | Science | [5 empty] | Requirements | N/A | N/A
FAR Clause | AO Selection | Clause 1852.237-72 (NDA clause) needs to be included in contracts for access to NASA IT systems (Windchill) |  | ESSP | CYGNSS |  | 2013-01-28 | [10 empty] | Science | [5 empty] | Requirements | N/A | N/A